## Action Items
Meeting Date | Item # | Minutes § Ref. | Action Item | Responsible Party | Target Due Date | Status | Responsible Party Response Date | [9 empty] | Notes
[7 empty] | USA | USAF | USMC | USN | DLA | DLA Tran. Svcs. | DLMSO | GSA | FAA | NOAA
From the FPRC Meeting Minutes of the March 4, 2015 (Click to Download)
2015-03-04 | 1 | 2. | Finance PRC Chair to staff a PDC introducing edits for DAAS - and all order processing entry points where order-initiating transactions do not route through DAAS - to reject transactions with invalid fund codes for all Components. | Chair | 2015-05-01 | Open | [10 empty] | DLMSO: (6/5) PDC 1043E expected to be staffed soon after June FPRC meeting.
2015-03-04 | 2 | 3.a.(1) | Components review PDC 1084 when released and respond to staffing notes. | Components | TBD | Open
2015-03-04 | 3 | 3.a.(2) | Components report to FPRC Chair the status of full Signal Code C/L implementation within their billing and feeder systems. | Components | 2015-04-30 | Open | [10 empty] | USAF: (5/15) Investigating
2015-03-04 | 4 | 3.a.(4) | DLA, GSA and other Sources of Supply are asked to evaluate standardizing the funds verification capability for use in ordering processes where the order entry point is other than the Component ordering system. | DLA, GSA and other Sources of Supply | Ongoing | Open
2015-03-04 | 5 | 3.a.(5) | Components are asked to evaluate using the funds verification capability in their processes and systems going forward. | Components | Ongoing | Open
2015-03-04 | 6 | 3.a.(6) | Defense Security Cooperation Agency (DSCA) and Security Cooperation Enterprise Solution (SCES) evaluate establishing fund codes for Business Partner Cases citing the correct LOA with beginning and ending periods of availability. Report findings to FPRC Chair. | DSCA & SCES | 2015-08-30 | Open | [10 empty] | DSCA Response: Pending
2015-03-04 | 7 | 3.a.(7) | ODCMO/OUSD(C) during the next BEA update complete business rule update to SFIS BR# 720604 for Beginning Period of Availability to allow use under no-year funds to represent Program Year. | ODCMO/OUSD(C) | TBD | Open | [10 empty] | OUSD(C)/DCMO Response: Pending
2015-03-04 | 8 | 3.a.(9) | DLMSO staff PDC 1043D to map limit/subhead to sub allocation on the Fund Code to Fund Account Conversion Table and change the heading name to sub allocation. | DLMSO | 2015-04-25 | Closed | [10 empty] | DLMSO: PDC staffed 5/28/2015.
2015-03-04 | 9 | 3.a.(14) | DLA complete draft PDC 1050A for EMALLcredit card failures, including documenting an interim process pending full implementation. | DLA | 2015-06-30 | Open
2015-03-04 | 10 | 3.a.(15) | Components/Sources of Supply evaluate all processes where individual document numbers are used in the ordering processes, but suppressed in the detail bill. Report results to FPRC Chair, along with impediments to producing proper detail bills in the near term. | Components/ Sources of Supply | 2015-06-30 | Open
2015-03-04 | 11 | 3.a.(15) | Finance PRC Chair coordinate a follow-on discussion between DLA, DLMSO, ODASD(SCI) and OUSD(C) to address concerns regarding the DLA Troop Support initiative to eliminate MIPRs that includes using a single MILSTRIP document number for multiple line items. | Chair | 2015-06-30 | Open | [10 empty] | 4/20/2015: Target date extended. DLA Troop Support is working alternatives prior to meeting.
2015-03-04 | 12 | 3.a.(16) | Components report to FPRC Chair if there are sufficient fund codes to assign a unique fund code to each multi-year appropriation to support processing in a legacy environment until full DLMS implementation has been achieved, along with any impediments to doing so. | Components | 2015-07-15 | Open
2015-03-04 | 13 | 3.a.(17) | Components report to FPRC Chair their implementation status for the DLMS credit adjustment process, along with target implementation timeline (if known). | Components | 2015-08-01 | Open
2015-03-04 | 14 | 3.a.(18) | FPRC Chair, in conjunction with DLA Transaction Services, provide sample transactions to Component FPRC leads to review and determine why default lines of accounting are being used. | Chair/DLA Transaction Services | 2015-08-01 | Open
2015-03-04 | 15 | 3.a.(18) | DLMSO develop an administrative change to DLMS Vol. 4, Appendix 2.2 for the DLA default line of accounting (limit 5CBX). | DLMSO | 2015-08-01 | Closed | [10 empty] | DLMSO: (5/28) Included as part of PDC 1043D staffed 5/28/2015.
2015-03-04 | 16 | 4.a. | DLA evaluate locally assigned identifiers (as used in STORES) for shipping points and initiate action with Components to coordinate assignment of legitimate DoDAACs. Report concurrently to DLMSO FPRC and DoDAAD PRC Chairs (financehq@dla.mil and DODAADHQ@DLA.MIL). | DLA | 2015-05-01 | Open
2015-03-04 | 17 | 4.a. | DLA report to FPRC Chair the feasibility of initiating DLMS supply status transactions for STORES orders. | DLA | 2015-07-30 | Open
2015-03-04 | 18 | 4.a. | Air Force confirm that the current STORES catalog is being used for ordering through USAF systems. Report to FPRC Chair the status of initiating Interfund billing procedures for STORES orders. | Air Force | 2015-07-30 | Open | [10 empty] | USAF: (5/11) Reported initial assement that STORES could incorporate Interfund billing. Air Force is developing requirements common to like initiatives (i.e. SOCOM).
2015-03-04 | 19 | 4.b. | DLA report to FPRC Chair any external business processes using EMALL MRA reporting functionality where an individual document number is not assigned to each line item in a commercial order, along with the format of the MRA. | DLA | 2015-07-30 | Open
2015-03-04 | 20 | 4.c. | DLA report feasibility of creating unique document numbers for each line item in an order for orders placed through vendor Websites (e.g. DLA Medical Prime Vendor Program). | DLA | 2015-08-01 | Open
2015-03-04 | 21 | 4.c. | DLA report the feasibility of using of the funds verification process to confirm funds availability and recording obligations in Component systems as a future enhancement. | DLA | 2015-09-30 | Open
2015-03-04 | 22 | 4.c. | DLA report to FPRC Chair if any DMLSS customers are receiving “rolled-up” detail bills using a pseudo document number. | DLA | 2015-07-15 | Open
2015-03-04 | 23 | 5.a. | Representatives of DLA, Air Force, Army (General Fund), and GSA coordinate removing Fund Code VA from the Army service code. | DLA, Air Force, Army (General Fund), and GSA | 2015-05-30 | Open | [10 empty] | USAF: (5/15) Parties are coordinating. All waiting to remove once last bill comes in.
2015-03-04 | 24 | 5.b. | Angel Sweetser send Karen Opie-Toler information on invalid Interfund bills for which reversal is being requested. Provide a copy to FPRC Chair. | Air Force | 2015-04-15 | Closed | [10 empty] | USAF: (5/15) Air Force is making progress on much of the bills, will provide once a final list is identified of reversals requiring DLA assistance. (6/11) Updated during FPRC that Ronnie Danniels of DFAS was instramental in identifying 48 questionable bills to be worked and provided to DLA.
2015-03-04 | 25 | 5.c. | Components identify billing offices from which billing adjustments have been requested but not accomplished in a timely manner and provide specific examples. | Components | 2015-08-01 | Open
2015-03-04 | 26 | 5.e. | FPRC Chair set up a conference call to evaluate the Air Force concerns over for some of their DoDAACs with improper Authority Codes and explore potential solutions. | Chair | 2015-05-15 | Open
2015-03-04 | 27 | 6. | All Components review the distributed MS Excel file listing DoDAACs identifying a DFAS center billing address in the DoDAAC TAC 3 and report to FPRC Chair if near-term changes to these business process may be made to comply with policy, if there any impediments and projected dates when these impediments might be overcome. | Components | 2015-09-30 | Open
2015-03-04 | 28 | 8. | Components and DFAS provide FPRC Chair their target DLMS implementation dates; DFAS additionally provide the contact information for the action officer assigned responsibility for coordinating DLMS implementation of DFAS systems. | Components and DFAS | 2015-04-30 | Open | [10 empty] | DFAS: Pending USAF: Pending
From the Draft FPRC Meeting Minutes of the June 11, 2015 (To Be Posted Soon)
2015-06-11 | 1 | 4.c. | OUSD(C) to provide the current known list of feeder systems being tracked for SLOA compliance to the FPRC Chair for distribution to FPRC representatives. | OUSD(C) | 2015-07-16 | Open
2015-06-11 | 2 | 5.b. | Navy validate if fund code 7M supporting Army is still needed. | Navy | 2015-08-31 | Open
2015-06-11 | 3 | 5.b. | DLA and other sources of supply report to FPRC Chair any billing system improperly citing F series DICs for non-Interfund billing and actions planned or taken, such as system change requests to comply with policy. | Components/ Sources of Supply | 2015-08-31 | Open
2015-06-11 | 4 | 7. | FPRC Chair will coordinate a meeting between DLMSO, DFAS, Air Force, Navy, and DLA to further investigate the issue of bills missing unit price and day of year. | Chair | 2015-08-31 | Open

## Filtering Instructions
How to use the filters:
1) To view which rows a particular party needs to respond to: a) Select the down arrow in the column header, b) hover the mouse over "Filter by Color", c) Select "No Fill"
2) To undo a column filter: a) Select the down arrow in the column header, b) Select the "Clear Filter From _____"