## PDCs in Development
Change # | Abbreviated Title | DEDSO Action Officer | For | Synopsis | Date Reserved | Notes | Needs X12 Code Approval Y/N | Update from Last Month | Internal Coordination due date | DLMS IC | Team
1369A | Increase Packaging Threshold | Austin | DLA Distribution | This change increases the cost threshold to remediate discrepant packaging for all service owned Non-Procurement materiel from $300 to $1000 per supply discrepancy report (SDR). The threshold for New Procurement for service owned materiel will remain at $300. | 2026-03-10 | Development | N | No Change | N/A | N/A | SDR
1421 | Optional Notes Display | Best | System Improvement | In the DoDAAD update application, add a checkbox to hide the notes field and only allow members of that Service series (e.g., Army) be able to see notes. In the eDAASINQ program, add a checkbox to allow display of the notes (if not restricted by series). | 2022-07-14 | Development | N | No Change |  |  | Data
1478 | Clarified Price Adjustments via DLMS Status Updates | Fuller | ASW(S) Memo | From ASD(S): To ensure disbursements and collection transactions can be matched to the correct obligation price without an additional status transaction, DEDSO is directed to initiate development of a long-term solution by updating DLM 4000.25 with clear and specific guidance on required system modifications and business rules for the processing of supply status transactions. | 2024-08-09 | Development | N | No Change |  |  | Supply
1492 | Mandatory Use of Shipment Status and Returns (Supply/SDR) | Fuller | WMS | The solution reinforces existing policy on transaction requirements for materiel sent to DLA Distribution Centers. The lack of advance notice of shipment (DLMS 856P/R/S) transactions will cause materiel to be suspended and materiel without a pre-positioned materiel receipt (DLMS 527D) transaction may cause materiel to be receipted under the incorrect materiel owner. The change updated five DLMS transactions with data fields to include a supply discrepancy reporting number to clearly associate transactions used to provide credit due to ownership changes and to alert owners of suspended materiel when those transactions are not available. | 12/15/2024/ 1/22/2026 | Internal staffing: 2/6/2026 with Sus: 2/13/2026 (Finalizing adjuidcating comments with DLA) Prepping for Format and signature | Y | No Change | 2026-02-13 | 527D, 527R, 940R, 867I, 945A | Supply/SDR
1493 | Funds Verification Alternative Capability and G-Invoicing Support | Davis | G-invoicing | When orders are made directly to a seller’s internet ordering system, supply process considers the scenario as “offline” as it bypasses the buyer’s ordering system with systemic recording of obligations and due-ins. This change builds on the funds verification capabilities of Approved DLMS Changes (ADC) 328 and 1068. | 2024-12-06 | Development, setting up meeting with DLA J8 to discuss requirements. Will need follow up meeting s with FEDMALL and DAAS | Unk | No Change |  |  | Finance
1496 | EDAASINQ Enhancements- Addition of Contact Point to EDAASINQ Query Screen | Best | System Improvement | Enhancement to the EDAASINQ | 2025-02-14 | Development | N | No Change |  | N/A | Data
1502 | Notification of Special Charges and Allowances | Davis | G-invoicing | A solution to make sure customers are made aware as soon as possible (i.e. after shipment) of special charges and allowances incurred as part of preparing materiel for shipment so the customer can review and update obligations before the charges arrive on the bill. | 2025-09-02 | Development | Unk | No Change |  |  | Finance
1511 | Synchronizing Revenue Recognition | Davis | G-invoicing | Documents steps to have DoD trading partners agree on timing to record revenue recognition to reduce risk of out-of-synch accounting steps which can impact eliminations. | 2025-08-06 | 4/2/26: Put on hold for proposal to single FOB(Source) flow. | N | Update |  | N/A | Finance
1514 | Air Force Implementation of 940R Version 4050 | Ferrari | FMS | Needed to support FMS Customers by providing additional prices on the DD Form 1348-1A | 2025-09-25 | Sent out for External Component Review | N | Update | 2026-03-04 | 940R | Supply
1515 | Product Identifier Inventory Adjustments for Government Furnished Property | Ferrari | GFP - Audit | Supports multi-adjustment of inventory data related to serialized GFP. | 2025-10-20 | Reviewing Internal Comments - pending feedback | Y | Update | 2026-03-20 | 947i | Supply
1516 | 527R Materiel Receipt Revisions | Gratkowski | WMS | Clarifies receipt cancellation, revision, and reversal processes within Warehouse Management System (WMS). Establishes process and timelines to support audit NFRs. | 2025-10-28 | Met with Dispo. Updating Dispo background per Dispo's request. Remaining issue with 947i. May be a topic at Tonja's Dipso WG | N | Update | 2026-02-17 | 527R | Supply
1517 | Update to DLMS 947I, Inventory Adjustment to support Government Furnished Property (Supply) | Carter | GFP - Audit | Adds addional data elements (CAGE, part number, NSN, model number) for better adjustment supporting documentation. | 2025-11-20 | Developing | Y | No Change |  | 947i | Supply
1518 | First Quarterly MFR Administrative Update ADC | Nace | Clean-up | Non-standards changing housekeeping | 2025-11-20 | Development | N | No Change |  |  | Lead
1520 | Update DLMS 945A for GFP Accountability | Fuller | GFP- Audit (F-35) | Property Enhancements within the DLMS 945A Materiel Release Advice. | 2025-11-27 | Internal Staffing Sus: (3/23/2026)-finalizing adjudication/prep for signature | Y | No change | TBD | 945A | Supply
1525 | Updates to DLMS 527R- Disposition Services | Carter | DLA Disposition | Updates to DLMS 527R- Disposition Services, 4000.25, V2, Ch 16 | 2026-02-26 | Development | N | No Change | TBD | 527R | Supply
1527 | Transshipment Process for Cargo Shipments using the 940R Transaction | Ferrari | DLMS Improvement | Updates to verbiage in Volume 3 to be consistent with logic implemented around Cargo Shipments within the ALC's | 2026-02-27 | Development | N | No Change | TBD | 940R/945A | Supply
1529 | New PDC to support DLA Disposition Services DLMS 527D | Carter | DLA Disposition | Updates required to support DLMS 4000.25, V2, C16 rewrite and Disposition Effort | 2026-03-12 | In Development | n | Update | TBD | 527D | Supply
1528 | Updates to the DLMS 846M Cataloging Demand Data | Carter | DLA EBS and Cataloging | Updates required to update the Implmentation Convention to modify data elements and useage | 2026-03-05 | In Development | Unk | No Change | TBD | 846M | Cataloging

## PDCs Signed
Change # | Abbreviated Title | DEDSO Action Officer | For | Synopsis | Date Reserved | Date PDC Signed | Notes | Update from Last Month | External Coordination Due | DLMS IC | Team
1443C | Product Quality Deficiency Reporting Policy Migration Updates | Breen | PQDR | This change continues the migration of DoD Product Quality Deficiency Reporting (PQDR) policy from the Joint Service Regulation (Reference 10.d.) to the Defense Logistics Manual (DLM) 4000.25. | 2024-08-09 | 2025-12-02 | Sent to ODASW(LOG) 3/18/2026. Waiting on signature. | Update
1505 | Supply Status Transaction Support for Offline Orders | Davis | G-invoicing | Supply Status Transaction Support for Offline Orders. Supports G-invoicing efforts. | 2025-06-30 | 2025-10-10 | DEDSO responses to commentors distributed. | Update
1513 | Interim Requirement Revisions to the DLMS 527R (Materiel Receipt) and DLMS 846R (Location Reconciliation Request) Transaction Sets | Nace | Clean-up | Revise multiple interim codes in DLMS 527R and 846M | 2025-09-11 | 2025-12-08 | Sent to OSW on 3/20/2026 | Update
1522 | Expand Usage of Item Unique Identification (IUID) in the DLMS 856S to Accommodate Ammunition Batch, Lot and Serial Number Data | Fuller | Army | Army requires shipment notification transactions to have the ability to transmit quantities at both the batch and serial number level of detail, where batch could contain one or more associated Serial Numbers, but the current DLMS 856S Implementation Convention does not support this requirement | 2026-01-23 | Signed 3/4/2026 and forward to the stakeholders with sus: 4/6/2026 | Y | No change |  | 856S | Supply
1523 | DLMS IC X12 Qualifier Updates (Supply) | Gratkowski/Zink | X12 Updates, Segregation Below the Line Item | Aligns DLMS IC X12 qualifiers with standard X12 qualifier | 2025-01-30 | 2026-03-26 | Sent out for External Component Review, due 27 April | Update | 2026-04-27 | 527D, 527R, 846R, 867I, 940R, 945A, 947I | Supply

## PDCs on Hold
| Abbreviated Title | DEDSO Action Officer | For | Synopsis | Date Reserved | DLMS Change Status | Update from Last Month | 2026-01-01
1170 | Clarify DOD Military Standard Billing System Requirement for Detail Document Number in Materiel Receipt Acknowledgment (MRA) for Tailored Vendor Relationship (TVR) | Davis | MRA | Clarify in DLMS, Volume 2 (Reference 3.a.), and Volume 4 (Reference 3.b.), the requirement for use of individual document numbers, in addition to contract, call, and delivery order line item numbers, with TVR MRA to support the existing DLMS, Volume 4, Military Standard Billing System requirement. | 2015-04-08 | Hold | No Change
1309 | Web Fund Code Data Quality Verification Improvements (Finance) | Davis | System Improvement | This DLMS change proposes modifications to the Web Fund Code application, used by Component-designated Fund Code Monitors to maintain their Component’s fund codes. It applies data integrity checks between entries in the Standard Financial Information Structure (SFIS) Fund Code to Fund Account Conversion Table (a.k.a. FCA table) and the Fund Code to Billed Office DoDAAC Table (a.k.a. FCB table, or Third-Party Billing Table). | 2018-03-13 | Hold | No Change
1358 | Update TAC in 940R IC | Best | WMS | Transportation Policy Updates | 2019-10-17 | Hold. Reviewing need with intitiator (DLA) and migration from DSS to WMS. | No Change
1413 | Remove Address Data from the Routing Identifier Code (Department of Defense Activity Address Directory) | Best | System Improvement | This change will remove the address elements from the Routing Identifier Code (RIC). The only postal address will be the Type of Address Code (TAC) 1 address in the Department of Defense Activity Address Code (DoDAAC) and the RIC will no longer carry the address elements. | 2021-06-09 | Hold. Dependancy on ADC 1263 which goes into full effect in Dec 2025. HOVER NOTE. | No Change
1426 | Remove Standard Point Location Code from DoDAAD | Best | System Improvement | Remove the SPLC data element from the DoDAAD database and update systems and reports that include the SPLC: (1) DoDAAD Update (2) DAASINQ (3) eDAASINQ (4) All reports on the DoDAAD Download and Reports page. | 2021-12-27 | Hold. Pending retirement of DSS & implementation of JTMS. HOVER NOTE. | No Change
1440 | DoDAAD to AAD. | Morrow | Clean-up | Name change to reflect usage outside of DoD | 2022-07-07 | Hold | No Change
1447 | Demand Reporting to Address Navy BHJ Transaction Requirements | Best | Navy | Navy specific for demand reporting. | 2022-11-10 | Hold | No Change
1448 | DoD Causative Research Thresholds | Fuller | WMS | Conversation with the Customer and the customer decided to put this one on hold | 2022-11-10 | Hold | No Change
1458 | Routing of Requisitions and Supply Status without Legacy Dependencies | Best | Clean-up | Removal of legacy MILSTRIP codes from the DLMS. | 2023-05-01 | Hold | No Change
1506 | DLMS X12 Maintenance Updates | Zink | Clean-up | The DLMS ICs have, over time, accumulated X12 data maintenance actions that were not completed in previous updates to the ICs. | 2025-07-03 | Awaiting DAAS requirements. | No Change
1508 | DLMS IC Code Collision Updates | Zink | Clean-up | This involves updating qualifiers for X12 actions with qualifier definition collisions | 2025-07-14 | Awaiting DAAS requirements. | No Change
1509 | SDR DLMS Data Maintenance Change Updates | Zink | Clean-up | This involves updating qualifiers for X12 actions with qualifier definition collisions and data maintnenance in the SDR ICs | 2025-07-14 | Awaiting DAAS requirements. | No Change
1455 | Removal of Passive Radio Frequency Identification References in DLM 4000.25 | Carter | OSW | Removal of Passive Radio Frequency Identification References in DLM 4000.25 |  | Awaiting OSW pRFID decision | No Change
1519 | DLMS 814R Cataloging update to support Action/Task ID | Carter | Cataloging | DLMS 814R Cataloging update to support Action/Task ID | 2025-11-20 | Awaiting FLIS requirement to proceed | No Change | Followed up 3/17/25
1043H | Revised Procedural Requirements for Hazardous Property Disposal Release Orders | Nace | Disposal | Establishes procedures required to properly distinguish excess personal property from hazardous property, which encompasses hazardous waste, hazardous material, and other materiel potentially containing hazardous material at the time of materiel disposition, related disposal release orders (DROs) to comply with Single Line of Accounting (SLOA) reporting requirements. | 2025-07-23 | Pending DLA determination on impacts to the auto-disposal process | No Change
Note on G5: We put this on ice because the Air Force still has orphaned RICs. Because of the edits that were already implemented for part ADC 1263, they cannot create new orphaned DoDAACs. ADC 1263 is supposed to go into full effect in December 2025, so we will either move forward with this PDC, or the PDC will become OBE because we will delete the independent RIC search function.
Note on G6: Current systems have a reliance upon SPLCs for non-contract shipments. Contract shipments are 99% of all movements, so this is a relatively small number, but DLA Distribution expressed concern about eliminating SPLCs in the even their 3PL contract is cancelled or a new contract is not issued.