## PDCs in Development
Change # | Abbreviated Title | DEDSO Action Officer | Synopsis | Date Reserved | Notes | Needs X12 Code Approval Y/N | Update from Last Month | 2025-08-01
1273 | Receipt Reversals | Breen | Supply Discrepancy Report (SDR) Disposition Instructions Authorizing Receipt Reversal for Receipts and Associated SDRs Submitted to the Wrong Owner and Use of Reason for Reversal Code on Receipt Transaction | N/A | We will withdraw ADC 1273. DLA's new WMS system does not have the capability to perform receipt revisions after an item is stowed in location. waiting on DLA to confirm/provide updated process. | N | No Change
1421 | Optional Notes Display | Morrow | In the DoDAAD update application, add a checkbox to hide the notes field and only allow members of that Service series (e.g., Army) be able to see notes. In the eDAASINQ program, add a checkbox to allow display of the notes (if not restricted by series). | 2022-07-14 | Development | N | No Change
1455 | Removal of pRFID References in DLMS Publications and Implementation Conventions | Morrow | This change removes Passive Radio Frequency Identification Devices (pRFID) references in DLMS publications and Implementation Conventions. | 2023-03-09 | Development | N | No Change
1478 | Clarified Price Adjustments via DLMS Status Updates | Fuller | From ASD(S): To ensure disbursements and collection transactions can be matched to the correct obligation price without an additional status transaction, DEDSO is directed to initiate development of a long-term solution by updating DLM 4000.25 with clear and specific guidance on required system modifications and business rules for the processing of supply status transactions. | 2024-08-09 | Development | N | No Change
1491 | Government Furnished Property Embed | Nace | Reports when an item of GFP is: 1. Embedded into another GFP item at individual or line level 2. Embedded into a production, non-GFP, item 3. Consumed | 2025-03-18 | Sent to ODASD(L) for signature 7/29/2025 | Unk | Update
1493 | Funds Verification Alternative Capability and G-Invoicing Support | Davis | When orders are made directly to a seller’s internet ordering system, supply process considers the scenario as “offline” as it bypasses the buyer’s ordering system with systemic recording of obligations and due-ins. This change builds on the funds verification capabilities of Approved DLMS Changes (ADC) 328 and 1068. | 2024-12-06 | Development | Unk | No Change
1496 | EDAASINQ Enhancements- Addition of Contact Point to EDAASINQ Query Screen | Morrow | Enhancement to the EDAASINQ | 2025-02-14 | Development | N | No Change
1500 | New Defense Logistics Management Standards 536R Transaction to Support Required Acquisition and Valuation Data Elements | Nace | Removes the Service Estimate Number code, used to indicate the estimated useful life of an item from 2/LDT01/1200, and creates a new equivalent code ER (Estimated Remaining Economic Life) in 2/QTY01/0400 to comply with the American National Standards Institute (ANSI), Accredited Standards Committee (ASC), X12 industry standard. | 2025-03-18 | Sent to ODASD(L) for signature 7/29/2025. Was 1415A. | Y | Update
1505 | Supply Status Transaction Support for Offline Orders | Davis | Supply Status Transaction Support for Offline Orders. Supports G-invoicing efforts. | 2025-06-30 | Development | Unk | No Change
1506 | DLMS X12 Maintenance Updates | Zink | The DLMS ICs have, over time, accumulated X12 data maintenance actions that were not completed in previous updates to the ICs. | 2025-07-03 | Development | Y | New
1508 | DLMS IC Code Collision Updates | Zink | This involves updating qualifiers for X12 actions with qualifier definition collisions | 2025-07-14 | Development | Y | New
1509 | SDR DLMS Data Maintenance Change Updates | Zink | This involves updating qualifiers for X12 actions with qualifier definition collisions and data maintnenance in the SDR ICs | 2025-07-14 | Development | Y | New
1510 | DLMS 832N Update for C-ICP Accountablity | Fuller | Add OM&S reportable valuation method ands coding for weapon system variants | 2025-07-16 | Development | N | New
1043H | Revised Procedural Requirements for Hazardous Property Disposal Release Orders | Nace | Establishes procedures required to properly distinguish excess personal property from hazardous property, which encompasses hazardous waste, hazardous material, and other materiel potentially containing hazardous material at the time of materiel disposition, related disposal release orders (DROs) to comply with Single Line of Accounting (SLOA) reporting requirements. | 2025-07-23 | Development | N | New
1512 | DLMS X12 Maintenance Updates | Zink | During the review process of the DLMS ICs, it was discovered that some data element names in the ICs didn't match the X12 database. | 2025-08-05 | Development | Y | New

## PDCs Signed
Change # | Abbreviated Title | DEDSO Action Officer | Synopsis | Date Reserved | Date DASD(L) Signed PDC | Notes | Update from Last Month | 2025-08-01
1483 | 867I Materiel Issue of Expended Ordnance | Nace | New change aimed at addressing three Navy NFRs. The change includes the addition of a new Ordnance Expenditure code to the Product Transfer Type Code in the DLMS 867I (Issue) Implementation Convention. Removal of internal Navy Ordnance Information System (OIS) processes and consolidation of reporting requirements into the 867I transaction will enable the Navy to streamline financial and inventory reporting based on expenditure scenarios. | 2024-09-30 | 2024-12-13 | Flipped to ADC. On hold pending ANSI X12 approval of new qualifiers. | No Change
1415A | New Defense Logistics Management Standards 536R Transaction to Support Required Acquisition and Valuation Data Elements | Nace | Removes the Service Estimate Number code, used to indicate the estimated useful life of an item from 2/LDT01/1200, and creates a new equivalent code ER (Estimated Remaining Economic Life) in 2/QTY01/0400 to comply with the American National Standards Institute (ANSI), Accredited Standards Committee (ASC), X12 industry standard. | 2025-03-18 | 2025-05-29 | This is canceled and will become PDC 1500 | Update
1465B | G-Invoicing Data Table for Redirected Requisitions | Davis | When a requisition to an initial source of supply is routed to another source of supply, the G-INV information on the original requisition is no longer valid. The October STWG meeting determined that the solution to Gap #4 needed an alternative solution than a table at DAAS to look-up GT&Cs when a requisition is referred to a different Component. The new draft PDC follows an assumption that seller systems will be able to infer the applicable GT&C based on the bill-to party of the requisition and will confirm the GT&C back to the buyer upon committing to service the requisition in whole or part. | 2024-08-20 | 2025-06-10 | Adjudicating comments | Update
1484 | Create Defense Logistics Management Standard 888N - Cataloging New Item | Morrow | Creates the DLMS 888N for FLIS Modernization. | 2024-11-01 | 2025-06-17 | Sent to ODASD(L) for final signature 8/11/2025 | Update
1485 | Create Defense Logistics Management Standard 888M - Cataloging Item Maintenance | Morrow | Creates the DLMS 888M for FLIS Modernization. | 2024-11-01 | 2025-06-17 | Adjudicating comments | Update
1486 | Create Defense Logistics Management Standard 814R - Cataloging Response | Morrow | Creates the DLMS 814R for FLIS Modernization. | 2024-11-01 | 2025-06-17 | Sent to ODASD(L) for final signature 8/8/2025 | Update
1487 | Create Defense Logistics Management Standard 846M - Cataloging Demand Transaction | Morrow | Creates the DLMS 846M for FLIS Modernization. | 2024-11-01 | 2025-06-17 | Sent to ODASD(L) for final signature 8/8/2025 | Update
1488 | Create Defense Logistics Management Standard 814D - Cataloging DEMIL Submission Adjustments | Morrow | Creates the DLMS 814D for FLIS Modernization. | 2024-11-01 | 2025-06-17 | Sent to ODASD(L) for final signature 8/8/2025 | Update
1489 | Create Defense Logistics Management Standard 888C - Cataloging Status Inquiry | Morrow | Creates the DLMS 888C for FLIS Modernization. | 2024-11-01 | 2025-06-17 | Sent to ODASD(L) for final signature 8/8/2025 | Update
1494 | Create Defense Logistics Management Standard 814C - Cataloging Collaboration Request/Response | Morrow | Creates the DLMS 814C for FLIS Modernization. | 2024-12-21 | 2025-06-17 | Sent to ODASD(L) for final signature 8/8/2025 | Update
1497 | Notification of Hazardous Waste Delivery Order and Shipping Status | Nace | Discussions with DLA Hazardous Material Management System – Hazardous Waste Disposition (HMMS-HWD) and DLA Disposition Services regarding a new DLMS transaction to exchange details regarding hazardous waste delivery order and shipping details. The data exchange will provide the information immediately necessary to eliminate situations where fines may be levied due to permit restrictions for some storage/removal location | 2/27/2025 | 2025-07-30 | With PRC for comments | Update
1501 | Key Supporting Document Inclusions for Government Furnished Property Audit Compliance | Nace | Adds case number information to the DLMS 947I to more accurartely record GFO inventory actions | 2025-04-01 | 2025-07-16 | With PRC for comments | Update

## PDCs on Hold
| Abbreviated Title | DEDSO Action Officer | Synopsis | Date Reserved | DLMS Change Status | Update from Last Month | 2025-08-01
1170 | Clarify DOD Military Standard Billing System Requirement for Detail Document Number in Materiel Receipt Acknowledgment (MRA) for Tailored Vendor Relationship (TVR) | Davis | Clarify in DLMS, Volume 2 (Reference 3.a.), and Volume 4 (Reference 3.b.), the requirement for use of individual document numbers, in addition to contract, call, and delivery order line item numbers, with TVR MRA to support the existing DLMS, Volume 4, Military Standard Billing System requirement. | 2015-04-08 | Hold | No Change
1309 | Web Fund Code Data Quality Verification Improvements (Finance) | Davis | This DLMS change proposes modifications to the Web Fund Code application, used by Component-designated Fund Code Monitors to maintain their Component’s fund codes. It applies data integrity checks between entries in the Standard Financial Information Structure (SFIS) Fund Code to Fund Account Conversion Table (a.k.a. FCA table) and the Fund Code to Billed Office DoDAAC Table (a.k.a. FCB table, or Third-Party Billing Table). | 2018-03-13 | Hold | No Change
1358 | Update TAC in 940R IC | Morrow | Transportation Policy Updates | 2019-10-17 | Hold. Reviewing need with intitiator (DLA) and migration from DSS to WMS. | No Change
1413 | Remove Address Data from the Routing Identifier Code (Department of Defense Activity Address Directory) | Morrow | This change will remove the address elements from the Routing Identifier Code (RIC). The only postal address will be the Type of Address Code (TAC) 1 address in the Department of Defense Activity Address Code (DoDAAC) and the RIC will no longer carry the address elements. | 2021-06-09 | Hold. Dependancy on ADC 1263 which goes into full effect in Dec 2025. HOVER NOTE. | No Change
1426 | Remove Standard Point Location Code from DoDAAD | Morrow | Remove the SPLC data element from the DoDAAD database and update systems and reports that include the SPLC: (1) DoDAAD Update (2) DAASINQ (3) eDAASINQ (4) All reports on the DoDAAD Download and Reports page. | 2021-12-27 | Hold. Pending retirement of DSS & implementation of JTMS. HOVER NOTE. | No Change
1440 | DoDAAD to AAD. | Morrow | Name change to reflect usage outside of DoD | 2022-07-07 | Development | No Change
1447 | Demand Reporting to Address Navy BHJ Transaction Requirements | Best | Navy specific for demand reporting. | 2022-11-10 | Hold | No Change
1448 | DoD Causative Research Thresholds | Fuller | Conversation with the Customer and the customer decided to put this one on hold | 2022-11-10 | Hold | No Change
1458 | Routing of Requisitions and Supply Status without Legacy Dependencies | Best | Removal of legacy MILSTRIP codes from the DLMS. | 2023-05-01 | Hold | No Change
1480 | Admin Update to DLM 4000.25 Volume 1 | Landon | In work with ODASD(L) on an admin update of DLM Volume 1 | 2024-08-23 | Development | No Change
1492 | Mandatory Use of Shipment Status and Returns (Supply/SDR) | Best/Fuller | The solution reinforces existing policy on transaction requirements for materiel sent to DLA Distribution Centers. The lack of advance notice of shipment (DLMS 856P/R/S) transactions will cause materiel to be suspended and materiel without a pre-positioned materiel receipt (DLMS 527D) transaction may cause materiel to be receipted under the incorrect materiel owner. The change updated five DLMS transactions with data fields to include a supply discrepancy reporting number to clearly associate transactions used to provide credit due to ownership changes and to alert owners of suspended materiel when those transactions are not available. | 2024-12-15 | DLA is collecting additional data and way forward discussion. | No Change
Note on F5: We put this on ice because the Air Force still has orphaned RICs. Because of the edits that were already implemented for part ADC 1263, they cannot create new orphaned DoDAACs. ADC 1263 is supposed to go into full effect in December 2025, so we will either move forward with this PDC, or the PDC will become OBE because we will delete the independent RIC search function.
Note on F6: Current systems have a reliance upon SPLCs for non-contract shipments. Contract shipments are 99% of all movements, so this is a relatively small number, but DLA Distribution expressed concern about eliminating SPLCs in the even their 3PL contract is cancelled or a new contract is not issued.